## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
Core architecture established — FastAPI service modules and Next.js frontend both delivered successfully integrated. A live Power BI dashboard was demonstrated using sample energy data. Team collaboration was effective. | Anomaly detection required refinement due to incorrect query aggregation and baseline calculations, producing inaccurate results | Introduce better validation checks in the analytics pipeline and improve backend logging to detect data inconsistencies | Implement residual-based anomaly scoring and update backend queries to correctly propagate thresholds and baseline values. Add anomaly validation tests
Dashboard developed with multiple analytics sections — energy trends, anomaly insights, forecasting, carbon analytics | The initial plan didn’t fully account for the integration needed for real-time services. | Improve KPI cards with clearer anomaly metrics and better labeling for aggregate vs device-level anomalies | Add Net Anomalies and Any-Device Anomaly Days KPI indicators; update visualisations to show anomaly severity and source attribution
Authentication with JWT + bcrypt and RBAC (Admin / User / Viewer) fully implemented | System initially lacked account management — no profile editing or password change features | Extend authentication module to include profile management and password change functionalities | Develop profile update and password change APIs; integrate with /profile and /change-password frontend pages
Analytics layer integrates energy trends, forecasting, anomaly detection, and carbon emission estimation | Cost calculations used inconsistent currency representations causing confusion in financial analytics | Standardise cost calculations using a consistent tariff model aligned with regional electricity pricing | Implement centralized tariff utility; update all analytics modules to compute cost using consistent INR tariff